## Sheet1
Cost Estimate
Project Name: | Date:
Using the 15% reduction in budget, adjust eacch column.
| Internal | $/hour | Internal | External | $/hour | External | Total | Non-labor $ | Original Total Cost | 15% Reduction | Project Change (Cost)
WBS Categories | Labor |  | $ Total | Labor |  | $ Total | Labor
1. Initiating | 200 | 65 | 13000 |  |  | 0 | 13000 |  | 13000 | 1950 | 11050
2. Planning | 600 | 60 | 36000 |  |  | 0 | 36000 |  | 36000 | 5400 | 30600
3. Executing |  |  | 0 |  |  | 0 | 0 |  | 0
3.1 Implementation and Integration |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.1 Hardware Installation | 600 | 60 | 36000 | 600 | 150 | 90000 | 126000 | 100000 | 226000 | 33900 | 192100
3.1.2 Software Installation/Licences | 300 | 55 | 16500 | 300 | 150 | 45000 | 61500 | 50000 | 111500 | 16725 | 94775
3.1.3 Infrastructure upgrades | 400 | 60 | 24000 | 400 | 150 | 60000 | 84000 | 50000 | 134000 | 20100 | 113900
3.1.4 Software applications training | 400 | 60 | 24000 | 400 | 150 | 60000 | 84000 | 50000 | 134000 | 20100 | 113900
3.2 Testing and Verification | 400 | 55 | 22000 | 300 | 250 | 75000 | 97000 | 80000 | 177000 | 26550 | 150450
3.3.System Acceptance | 300 | 55 | 16500 |  |  | 0 | 16500 |  | 16500 | 2475 | 14025
3.4 System Migration | 300 | 55 | 16500 |  |  | 0 | 16500 |  | 16500 | 2475 | 14025
4. Monitoring and Controlling | 500 | 55 | 27500 |  |  | 0 | 27500 |  | 27500 | 4125 | 23375
5. Closing | 200 | 55 | 11000 |  |  | 0 | 11000 |  | 11000 | 1650 | 9350
Subtotal | [8 empty] | 903000 | 135450 | 767550
Reserves |  |  | 0 |  |  | 0 | 0 |  | 90300
Total | 4200 |  | 243000 | 2000 | 850 | 330000 | 573000 | 330000 | 993300 | 270900 | 767550
B. Desciribe the 3 impacts this will have on your project.
i. The testing staffs will be reduced
ii. We will buy cheaper hardware or servers
iii. The system monitoring period will be shorten
C. Name three other things outside of the project plan/schedule need consideration?
i. how much performance of the software will be affected if we cut the budget on hardware
ii. How much risk for software failure in production if we cut testing period
iii. How could we ensure the software runs and hand over to customer smoothly without any issues happen
D. What changes will you make to save the project? Describe and justify your choices in detail.
1. We will cut the testing staffs and using outsouce to test our project, this can save money on testing and not have to pay mutiple staffs
2. We will buy cheaper servers, this may affect some performance of the actual software
3. We will cut the testing time frame because there is not enough budget for enough testing